## PP V1.2
Week 2:
Task | Assigned to | Task Duration | Start Date | End Date | Update
Project Plan | Hager AbdelAal | 3 hours | 2023-09-02 | 2023-09-02
SIQ | Radwa Magdi | 4 hours | 2023-09-02 | 2023-11-02
CRS | Doaa Maher & Kareem Murad | 8 hours | 2023-09-02 | 2023-11-02 | Updated by Radwa Magdi (16/2/2023)
HIS | Peter Ghali | 6 hours | 2023-10-02 | 2023-11-02
RTM | Hady Sallam | 4 hours | 2023-10-02 | 2023-11-02
Week 3:
Task | Assigned to | Task Duration | Start Date | End Date
SRS | Hager AbdelAal | 5 hours | 16/2/2023 | 17/2/2023
CRS Update | Radwa Magdi | 4 hours | 16/2/2023 | 17/2/2023
PP Update | Hager AbdelAal | 1 hours | 15/2/2023 | 16/2/2023
Week 4:
Task | Assigned to | Task Duration | Start Date | End Date
Update SRS | Hager AbdelAal | 3 hours | 2023-05-03 | 2023-10-03
CRS Review | Hady Sallam | 1 hours | 2023-05-03 | 2023-10-03
GDD | Kareem Murad & Peter Ghali | 8 hours | 2023-05-03 | 2023-10-03
Week 5:
Task | Assigned to | Task Duration | Start Date | End Date
Update PP | Hager AbdelAal | 1 hours | 15/3/2023 | 17/3/2023
CDD | Doaa Maher & Radwa Magdi | 8 hours | 15/3/2023 | 18/3/2023
Week 6:
Task | Assigned to | Task Duration | Start Date | End Date
Implementation | All team members | 3 days | 20/3/2023 | 26/3/2023